## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
Tasks
As a hotel owner I want an online Payment option on my website so that I can process online payments

## Product Backlog - Meeting 2
Product Backlog | Bus Value | Effort | ROI
As a customer I want to have member booking so that I can get special discounts off my booking | 40 | 0.5 | 80
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 1 | 40
As a hotel customer I want a webpage details page so that I can view my payment status | 40 | 2 | 20
As a customer I want to have member booking so that I do not have to remember my contact info | 8 | 0.5 | 16
As a payment provider I want an Payment API available so that I can see all payments on a date | 5 | 0.5 | 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 40 | 5 | 8
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 20 | 5 | 4
As a hotel customer I want a user portal so that I can cancel my booking | 20 | 5 | 4
As a hotel customer I want a user portal so that I can edit my booking | 20 | 5 | 4
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 40 | 20 | 2
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 40 | 20 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 20 | 2
As a owner I want to support loyality points to that customers can redeem for a deal | 20 | 20 | 1
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 40 | 40 | 1
As a hotel owner I want a payment details portal so that I can assist my customers | 2 | 3 | 0.66667
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 8 | 20 | 0.4
As a payment provideer I want a payment API that can hamdle different tax rates | 5 | 20 | 0.25
Note on D15: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 2
Effort is assumed out of 10
As a customer I want to have member booking so that I can get special discounts off my booking
Tasks | Effort
Create Database of members | 5
Use customer ID for authentication | 4
Make an API Call to fetch details | 7
Consult financial and marketing teams for offers that they can offer | 9
Integrate new offers to the website | 4
Allow redemption by members | 6
Integrate new offers to the website | 6
Integration Testing | 3
Exit Criteria - Done
Offers on website represents financial and market team input
Customer object as a member can redeem discount
Discount reflected on customers portal
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Effort
Create a database for payment details
Fetch payment information for all customers
create report database for posting payment details
transfer the fetched info into the report databse
give the access of the report database only to the payment provider/s
Validate connectivity
Integration Testing
Exit Criteria - Done
Test output data with actual information - Returns success
Report generated
As a hotel customer I want a webpage details page so that I can view my payment status
Tasks | Effort
Create a database for payment details and customer details
Fetch payment information for a customer by joining both databases with Customer_id
create webpage for posting payment details
Integrate databases with webpage
Print the results fetched in the webpage
Validate connectivity
Integration Testing
Exit Criteria
Display Output based on customer ID in the payment details and customer details database
As a customer I want to have member booking so that I do not have to remember my contact info
Tasks | Effort
Use the already existing member database
Fetch the contact information of the customer
Authenticate customer based on customer id and password
Make an api call to fetch the details to the web page
Validate connectivity
Integration testing
Exit Criteria
Customer does not have to write their contact info when logging in as a member
Note on B7: Dan Penny: Create taskss breakdown for 4 stories with top ROI

## Team Members
Name | A# | Role
Person 1 | A00431571 | Product Owner
Person 2 | A00428036 | ScrumMaster
Person 3 | A00427876 | Team Member
Person 4 | A00426488 | Team Member
Person 5 | A00430095 | Team Member
Person 6 |  | Team Member