## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
Tasks
As a hotel owner I want an online Payment option on my website so that I can process online payments

## Product Backlog - Meeting 2
Product Backlog | Bus Value | Effort | ROI
As a customer I want to have member booking so that I can get special discounts off my booking | 40 | 0.5 | 80
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 1 | 40
As a hotel customer I want a webpage details page so that I can view my payment status | 40 | 2 | 20
As a customer I want to have member booking so that I do not have to remember my contact info | 8 | 0.5 | 16
As a payment provider I want an Payment API available so that I can see all payments on a date | 5 | 0.5 | 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 40 | 5 | 8
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 20 | 5 | 4
As a hotel customer I want a user portal so that I can cancel my booking | 20 | 5 | 4
As a hotel customer I want a user portal so that I can edit my booking | 20 | 5 | 4
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 40 | 20 | 2
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 40 | 20 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 20 | 2
As a owner I want to support loyality points to that customers can redeem for a deal | 20 | 20 | 1
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 40 | 40 | 1
As a hotel owner I want a payment details portal so that I can assist my customers | 2 | 3 | 0.66667
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 8 | 20 | 0.4
As a payment provideer I want a payment API that can hamdle different tax rates | 5 | 20 | 0.25
Note on D23: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 2
Effort is assumed out of 10
As a customer I want to have member booking so that I can get special discounts off my booking
Tasks | Effort
Create Database of members | 5
Use customer ID for authentication | 4
Make an API Call to fetch details | 7
Consult financial and marketing teams for offers that they can offer | 9
Integrate new offers to the website | 4
Allow redemption by members | 6
Integrate new offers to the website | 6
Integration Testing | 3
3
Exit Criteria - Done
Offers on website represents financial and market team input
Customer object as a member can redeem discount
Discount reflected on customers portal
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Effort
Create a database for payment details | 5
Fetch payment information for all customers | 3
create report database for posting payment details | 5
transfer the fetched info into the report databse | 3
give the access of the report database only to the payment provider/s | 3
Validate connectivity | 8
Integration Testing | 3
Exit Criteria - Done
Test output data with actual information - Returns success
Report generated
As a hotel customer I want a webpage details page so that I can view my payment status
Tasks | Effort
Create a database for payment details and customer details | 5
Fetch payment information for a customer by joining both databases with Customer_id | 4
create webpage for posting payment details | 7
Integrate databases with webpage | 4
Print the results fetched in the webpage | 2
Validate connectivity | 5
Integration Testing | 3
Exit Criteria
Display Output based on customer ID in the payment details and customer details database
As a customer I want to have member booking so that I do not have to remember my contact info
Tasks | Effort
Use the already existing member database | 1
Fetch the contact information of the customer | 4
Authenticate customer based on customer id and password | 6
Make an api call to fetch the details to the web page | 2
Validate connectivity | 5
Integration testing | 3
Exit Criteria
Customer does not have to write their contact info when logging in as a member
Note on B7: Dan Penny: Create taskss breakdown for 4 stories with top ROI

## Sprint Backlog 3 - Meeting 3
Product Backlog | Bus Value | Effort | ROI
As a customer I want to have member booking so that I can get special discounts off my booking | 40 | 0.5 | 80
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 1 | 40
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 20 | 0.5 | 40
As a hotel customer I want a webpage details page so that I can view my payment status | 40 | 2 | 20
As a customer I want to have member booking so that I do not have to remember my contact info | 8 | 0.5 | 16
As a hotel owner I want to see the resurant menu so that customers will know what food options there are | 8 | 0.5 | 16
As a payment provider I want an Payment API available so that I can see all payments on a date | 5 | 0.5 | 10
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices) | 5 | 0.5 | 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 40 | 5 | 8
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 20 | 5 | 4
As a hotel customer I want a user portal so that I can cancel my booking | 20 | 5 | 4
As a hotel customer I want a user portal so that I can edit my booking | 20 | 5 | 4
As a customer I want to have an option to book a meeting hall so that I can online book an event | 20 | 5 | 4
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 20 | 5 | 4
As a hotel owner I want a special role so that I can have different access for different users ( admin/users) | 20 | 8 | 2.5
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 40 | 20 | 2
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 40 | 20 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 20 | 2
As a customer I want to get an email notification of payment so that I can have proof of payment | 40 | 20 | 2
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 40 | 20 | 2
As a owner I want to support loyality points to that customers can redeem for a deal | 20 | 20 | 1
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 40 | 40 | 1
As a hotel owner I want a payment details portal so that I can assist my customers | 2 | 3 | 0.66667
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 8 | 20 | 0.4
As a payment provideer I want a payment API that can hamdle different tax rates | 5 | 20 | 0.25
Note on D23: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 3
Effort is assumed out of 10
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle
Tasks | Effort
Tasks | Effort
Add a hyperlink on website for airport pickup | 1
Create a web page that takes customer itinerary | 2
Create a Schedule table in database consisting of customer information | 1
Check whether the customer ID exists in Schedule table. If not, create a new entry for customer | 1
Retrieve pickup schedule for individual customers by referencing the primary key, ID from Schedule Table | 1
Add functions for validation of customer input as per hotel requirements | 2
Set function to update details | 5
Add portal in website for customer to input details | 7
Integrate portal with data base | 7
Integration testing | 3
Exit Criteria
Succesful update of existing schedule
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices)
Tasks | Effort
Task | Effort
Add a link on website for previous payments | 1
Create a web page that displays previous payments | 3
Create a table, Flights for storing all flight bookings of a customer in database | 1
Retreieve past payment details based on customer ID from table Flights | 4
Integrate website page with database | 1
Display in tabular format on website page | 8
Add dropdown menu for each transaction to reveal a detailed summary of each transaction | 2
Integration testing | 3
Exit criteria
Customer can view all past details
Customer can view detailed summary of each transaction
Website link must work
Website must be integrated with database
As a hotel owner I want to see the resurant menu so that customers will know what food options there are
Tasks | Effort
Task | Effort
Get menu from restaurants in Hotel | 1
Define and build Menus Schema | 4
Integrate database with website | 7
Add menus to database | 2
Build portal in website | 3
Update portal information | 4
Integrate database with website
exit criteria
Restaurant menu uploaded on website
Restaurant menu viewable on website
pop-up the offers available in different restaurent of hotel
pop-up the offers available in different restaurent of hotel according to their previous preferences
make web page for menu and retrive the menu from database and populate it
interactive webpage with Marquee(showing specail meals offered in the different restaurents)
As a payment provider I want an Payment API available so that I can see all payments on a date
Tasks | Effort
Task | Effort
Design the API Strucure | 3
Build the API Structure | 4
Build the Payment Retrieve Function | 7
Output Results in tabular fashion | 3
Connect the API to the payment providers website | 2
Integration Testing | 3
Exit Criteria
Provider can view the details on a date on website

## Sprint Backlog 4 - Meeting 4
Product Backlog | Bus Value | Effort | ROI
As a customer I want to have member booking so that I can get special discounts off my booking | 40 | 0.5 | 80
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 1 | 40
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 20 | 0.5 | 40
As a hotel customer I want a webpage details page so that I can view my payment status | 40 | 2 | 20
As a customer I want to have member booking so that I do not have to remember my contact info | 8 | 0.5 | 16
As a hotel owner I want to see the resurant menu so that customers will know what food options there are | 8 | 0.5 | 16
As a payment provider I want an Payment API available so that I can see all payments on a date | 5 | 0.5 | 10
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices) | 5 | 0.5 | 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 40 | 5 | 8
As a customer I want events tab on the website so that I can get information on ongoing and scheduled evernts | 40 | 5 | 8
As a hotel owner I want to provide a complementary option for the first 5% of customers(per day) so that I can attract more customers | 10 | 2 | 5
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 20 | 5 | 4
As a hotel customer I want a user portal so that I can cancel my booking | 20 | 5 | 4
As a hotel customer I want a user portal so that I can edit my booking | 20 | 5 | 4
As a customer I want to have an option to book a meeting hall so that I can online book an event | 20 | 5 | 4
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 20 | 5 | 4
As a hotel owner I want a user portal so that customers can book activities that hotels offer at the spa | 20 | 5 | 4
As a customer I want to be able to login using social media so that they have easy access | 20 | 5 | 4
As a hotel owner I want a special role so that I can have different access for different users ( admin/users) | 20 | 8 | 2.5
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 40 | 20 | 2
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 40 | 20 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 20 | 2
As a customer I want to get an email notification of payment so that I can have proof of payment | 40 | 20 | 2
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 40 | 20 | 2
As a hotel owner I want a search option based on dates so that customer can see room availibility | 40 | 20 | 2
As a owner I want to support loyality points to that customers can redeem for a deal | 20 | 20 | 1
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 40 | 40 | 1
As a hotel owner I want a to provide the customer with a flexible refund process so that they can get instant refund in terms of points | 20 | 20 | 1
As a hotel owner I want my website to have B2B so that I connect to travel agents to offer them discouted rates | 40 | 40 | 1
As a hotel owner I want a payment details portal so that I can assist my customers | 2 | 3 | 0.66667
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 8 | 20 | 0.4
As a payment provideer I want a payment API that can hamdle different tax rates | 5 | 20 | 0.25
Note on D28: Dan Penny: Update Bus Value and Effort and ROI for all values

## Spring Backlog 4
Effort is assumed out of 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals
Tasks | Effort
Create Booking Alert Schema | 4
Source the booking alerts from the different locations from respective hotel APIs | 4
Add new deals portal to owner side of website | 7
Install live update notification in website for users | 3
Test the API integration | 4
Customise the alert for the loggedin loyal customers | 8
Do A/B testing of the deals for higher conversion rate | 6
Finalize the deals placement | 3
New deals show up on website | 1
Exit Criteria
New deals show up on website
API errors are clearly spelled.
Send an automated email to administrator for any errors.
As a customer I want events tab on the website so that I can get information on ongoing and scheduled events
Tasks | Effort
Create event database | 4
Add events to database | 2
Add events section in a prominent place on the website | 4
Integrate the website and database | 8
Integration testing | 3
Test for overflow and proper scroling on different device sizes and browsers. | 2
Exit Criteria
Customer can see events
Customer can click a link to see event on a new tab if the event fails to show
Send an automated email to administrator for any errors.
As a hotel owner I want to provide a complementary option for the first 5% of customers(per day) so that I can attract more customers
Tasks | Effort
Get All information from the customer bookings database | 2
Count the average number of bookings per day to estimate 5% for the future days | 1
Apply the function to the database to grab only the first 5% of bookings for the next day | 2
Build an advertisement banner for the website that showcases the offer | 4
Add the function in the website to apply complementary offer for the first 5% customers per day | 6
Integrate the website and the database | 7
Integration Testing | 3
Exit Criteria - Done
Succesfully offer complementary option to first 5% of customers per day
Successfully added the complemntary offer to the first 5% of customers per day
Database of Customers and Customers website assume existed.
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly
Tasks | Effort
Securely access the bookings database | 2
Grab All information from the bookings database | 6
add function to sort the bookings according to their customer ID | 7
Add the sorted bookings to a new table | 5
Integrate tabular format to showcase the customer booking transactions | 8
In the customer portal, allow customer to access the tables showcasing their transactions | 3
Integration Testing | 3
Exit Criteria - Done
Succesful viewing of all transactions in customer portal
Data retrieved successfully from Payment provider to be displayed
Verification of user

## Retrospective Meeting
Name | Role | What worked within the project | What did not work within the project
Bharat Bhushan Verma | Product Owner | The team showed great effort and outstanding output | Slight discrepency between what was expected and what was given
Mohd Nawaz Hussain | ScrumMaster | The tasks were divided according to everyone's strengths | Lack of communication at times was an issue
Kothai Kannappan Murugappan | Team Member | The output was better than expected given the timeframe | Timeframe was challenging
Ashwin Sivaraman | Team Member | Great communication between the team members | There was confussion regarding the requirements obtained from the hotel owner
Sarbottam Thapa Magar | Team Member | Development was smooth due to knowledge and past experience of the team members | Time constraints hampered the work quality

## Team Members
Name | A# | Role | Name
Person 1 | A00431571 | Product Owner | Bharat Bhushan Verma
Person 2 | A00428036 | ScrumMaster | Mohd Nawaz Hussain
Person 3 | A00427876 | Team Member | Kothai Kannappan Murugappan
Person 4 | A00426488 | Team Member | Ashwin Sivaraman
Person 5 | A00430095 | Team Member | Sarbottam Thapa Magar