## Product Backlog - Meeting 1
Product Backlog | Bus Value | Effort | ROI
As a payment provider I want an accept Payment API available so that I can provide my services to online stores |  |  | 3.35
As a payment provider I want an Payment API available so that I can troubleshoot payment issues |  |  | 3.7
As a payment provider I want an Payment API available so that I can see all payments on a date |  |  | 3.92
As a payment provider I want Payment info in a database so that I can see all my data for reports |  |  | 5.1
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly |  |  | 4.7
As a hotel customer I want a webpage details page so that I can view my payment status |  |  | 3.3
As a hotel owner I want a payment details portal so that I can assist my customers |  |  | 6.53
As a hotel customer I want a user portal so that I can cancel my booking |  |  | 2.88
As a hotel customer I want a user portal so that I can edit my booking |  |  | 1.8

## Sprint Backlog 1
Product Backlog | Avg Bus V | Avg Effort | ROI
As a hotel customer I want a webpage page so that I can make online payment
As a hotel owner I want an online Payment option on my website so that I can process online payments
As a hotel customer I want a webpage page so that I can make online payment
Tasks | Effort
Define and Build Database schema | 8
Define (processPayment) API call | 8
Build API call - integrate with service | 3
Test API call - manual test for postman | 2
Integrate API with existing site | 2
Create form for entering Process Payment params | 3
Validation prior to sumbission | 2
Section for transaction results | 3
Integrate Testing | 3
Exit Criteria - Done
Sucessful payment
field vaidations
insufficient funds
Assume we have a website, assume guest reservation
Tasks
As a hotel owner I want an online Payment option on my website so that I can process online payments

## Product Backlog - Meeting 2
Product Backlog | Bus Value | Effort | ROI
As a customer I want to have member booking so that I can get special discounts off my booking | 40 | 0.5 | 80
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 1 | 40
As a hotel customer I want a webpage details page so that I can view my payment status | 40 | 2 | 20
As a customer I want to have member booking so that I do not have to remember my contact info | 8 | 0.5 | 16
As a payment provider I want an Payment API available so that I can see all payments on a date | 5 | 0.5 | 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 40 | 5 | 8
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 20 | 5 | 4
As a hotel customer I want a user portal so that I can cancel my booking | 20 | 5 | 4
As a hotel customer I want a user portal so that I can edit my booking | 20 | 5 | 4
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 40 | 20 | 2
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 40 | 20 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 20 | 2
As a owner I want to support loyality points to that customers can redeem for a deal | 20 | 20 | 1
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 40 | 40 | 1
As a hotel owner I want a payment details portal so that I can assist my customers | 2 | 3 | 0.66667
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 8 | 20 | 0.4
As a payment provideer I want a payment API that can hamdle different tax rates | 5 | 20 | 0.25
Note on D23: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 2
Effort is assumed out of 10
As a customer I want to have member booking so that I can get special discounts off my booking
Tasks | Effort
Create Database of members | 5
Use customer ID for authentication | 4
Make an API Call to fetch details | 7
Consult financial and marketing teams for offers that they can offer | 9
Integrate new offers to the website | 4
Allow redemption by members | 6
Integrate new offers to the website | 6
Integration Testing | 3
3
Exit Criteria - Done
Offers on website represents financial and market team input
Customer object as a member can redeem discount
Discount reflected on customers portal
As a payment provider I want Payment info in a database so that I can see all my data for reports
Tasks | Effort
Create a database for payment details | 5
Fetch payment information for all customers | 3
create report database for posting payment details | 5
transfer the fetched info into the report databse | 3
give the access of the report database only to the payment provider/s | 3
Validate connectivity | 8
Integration Testing | 3
Exit Criteria - Done
Test output data with actual information - Returns success
Report generated
As a hotel customer I want a webpage details page so that I can view my payment status
Tasks | Effort
Create a database for payment details and customer details | 5
Fetch payment information for a customer by joining both databases with Customer_id | 4
create webpage for posting payment details | 7
Integrate databases with webpage | 4
Print the results fetched in the webpage | 2
Validate connectivity | 5
Integration Testing | 3
Exit Criteria
Display Output based on customer ID in the payment details and customer details database
As a customer I want to have member booking so that I do not have to remember my contact info
Tasks | Effort
Use the already existing member database | 1
Fetch the contact information of the customer | 4
Authenticate customer based on customer id and password | 6
Make an api call to fetch the details to the web page | 2
Validate connectivity | 5
Integration testing | 3
Exit Criteria
Customer does not have to write their contact info when logging in as a member
Note on B7: Dan Penny: Create taskss breakdown for 4 stories with top ROI

## Sprint Backlog 3 - Meeting 3
Product Backlog | Bus Value | Effort | ROI
As a customer I want to have member booking so that I can get special discounts off my booking | 40 | 0.5 | 80
As a payment provider I want Payment info in a database so that I can see all my data for reports | 40 | 1 | 40
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle | 20 | 0.5 | 40
As a hotel customer I want a webpage details page so that I can view my payment status | 40 | 2 | 20
As a customer I want to have member booking so that I do not have to remember my contact info | 8 | 0.5 | 16
As a hotel owner I want to see the resurant menu so that customers will know what food options there are | 8 | 0.5 | 16
As a payment provider I want an Payment API available so that I can see all payments on a date | 5 | 0.5 | 10
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices) | 5 | 0.5 | 10
As a customer I want to get alerts on bookings and new deals so that I can know about deals | 40 | 5 | 8
As a payment provider I want customer specific portal so that my customers can look at their transaction data directly | 20 | 5 | 4
As a hotel customer I want a user portal so that I can cancel my booking | 20 | 5 | 4
As a hotel customer I want a user portal so that I can edit my booking | 20 | 5 | 4
As a customer I want to have an option to book a meeting hall so that I can online book an event | 20 | 5 | 4
As a customer I want to schedue an airport pickup so that I be picked up by the hotel airport shuttle | 20 | 5 | 4
As a hotel owner I want a special role so that I can have different access for different users ( admin/users) | 20 | 8 | 2.5
As a payment provider I want an accept Payment API available so that I can provide my services to online stores | 40 | 20 | 2
As an owner I want to see what my customers are looking at so that I can provide customer specific offers | 40 | 20 | 2
As an owner I want to review/feedback page visible by owner so that I can improve customer satisfaction | 40 | 20 | 2
As a customer I want to get an email notification of payment so that I can have proof of payment | 40 | 20 | 2
As a hotel owner I want to implement a live chat for employees so that I can assist my customers in real time | 40 | 20 | 2
As a owner I want to support loyality points to that customers can redeem for a deal | 20 | 20 | 1
As an owner I want to support A/B testing so that I can optimize ad placement for revenue | 40 | 40 | 1
As a hotel owner I want a payment details portal so that I can assist my customers | 2 | 3 | 0.66667
As a payment provider I want an Payment API available so that I can troubleshoot payment issues | 8 | 20 | 0.4
As a payment provideer I want a payment API that can hamdle different tax rates | 5 | 20 | 0.25
Note on D23: Dan Penny: Update Bus Value and Effort and ROI for all values

## Sprint Backlog 3
Effort is assumed out of 10
As a customer I want to re-schedue an airport pickup so that I be picked up by the hotel airport shuttle
Tasks | Effort
Retrieve pickup schedule for customer by ID from Schedule Table | 1
Set function to update details | 5
Add portal in website for customer to input detail | 7
Integrate portal with data base | 7
Integration testin | 3
3
Exit Criteria
Succesful update of existing schedule
As a customer I want to see my pervious bookings so that I can see what I paid ( compare prices)
Tasks | Effort
Retreieve past payment details based on customer ID | 4
Put into tabular format in website | 8
Add section to payment portal in customer side of the website | 3
Show generated report | 1
Exit Criteria
Customer can view all past details
As a hotel owner I want to see the resurant menu so that customers will know what food options there are
Tasks | Effort
Get menu from restaurants in Hotel | 1
Add Menus database | 4
Integrate database with website | 7
Add menus to database | 2
Build portal in website | 3
Update portal information | 4
exit criteria
Restaurant menu uploaded on website
Restaurant menu viewable on website
As a payment provider I want an Payment API available so that I can see all payments on a date
Tasks | Effort
Retreive information from Payment API Already created | 3
Sort the payments according to date | 2
Store the information on a particular date in tabular format | 5
Build Payment API portal option with date selection | 7
Connect API to the new functionaility | 2
Exit Criteria
Provider can view the details on a date on website

## Team Members
Name | A# | Role
Person 1 | A00431571 | Product Owner
Person 2 | A00428036 | ScrumMaster
Person 3 | A00427876 | Team Member
Person 4 | A00426488 | Team Member
Person 5 | A00430095 | Team Member
Person 6 |  | Team Member